## Form 5 - AGDAR
FDP Form 5 - Annual GAD Accomplishment Report
(PCW-DILG-DBM-NEDA JMC No. 2016-01 dated January 12, 2016, Annex E)
ANNUAL GENDER AND DEVELOPMENT (GAD) ACCOMPLISHMENT REPORT
REGION: | REGION III - CENTRAL LUZON |  | CALENDAR YEAR: | 2024
PROVINCE: | TARLAC
CITY/MUNICIPALITY: | MONCADA
[6 empty] | Total LGU Budget: | 500000000
[6 empty] | Total GAD Expenditure: | 28840056.15
Gender Issue or GAD Mandate (1) | GAD Objective (2) | Relevant LGU Program or Project (3) | GAD Activity (4) | Performance Indicator and Target (5) | Actual Results (6) | Approved GAD Budget (7) | Actual Cost or GAD Expenditure (8) | Variance or Remarks (9)
CLIENT-FOCUSED
Gender Issue
200 men and women identified with tuberculosis cases and Lack of awareness of men and women infected with tuberculosis | To lower down the number of of men and women infected with TB | TB DOTS Program, TB DOTS drugs, conduct information, education campaign | Monitoring of family members with common symptoms of tuberculosis, Treatment of patients with tuberculosis, Distributionof IEC materials | 200 men and women treated with 100% success rate for 6 months | 203 men and women are receiving treatment for anti-tuberculosis. | 300000 | 300000 | Acccoplishments increases due to active TB screening.
High number of unemployed youth | To conduct skills and livelihood training that enhances the skills that will lead to independence for work. | Livelihood Training for YO and OSY | Conduct a livelihood training for youth organizations and Out-of-school youths. | 14 youth organization representatives and 37 OSYs (November 5, 2024) | Conducted Livelihood Training on Meat Processing attended by 25 OSYs on November 15, 2024 at Supreme Culinary School | 70000 | 90050 | Implemented
High number of youth using narcotic substances such as cigarretes and other illegal drugs | To decrease the number of youths using narcotic substances and other illegal drugs | Anti-drug Abuse Seminar | Information and dissemination campaign on using narcotic subtances and other illegal drugs | 1 orientation/seminar on Anti-Narcotics and Anti-Drugs Abuse 100-150 participants.(June 26, 2024) | PNP - Lecture/Symposium/ Seminar on Illegal Drugs were conducted to 37 Brgy | 20000 | 20000 | Implemented
High numberof dengue cases | To decrease the number of dengue cases | Kalinisan Kontra-Dengue Campaign | Conduct a clean-up drive activity where high number of dengue cases happen | Kalinisan Kontra Dengue activity to be conducted in selected barangays. 100-150 participants.(June 15, 2024) | Conducted a simultaneous clean-up drive participated by the 37 barangays | 50000 | 50000 | Implemented
High rate of youth struggling to find jobs after they leave school | Decrease unemployment among youths that already graduated | Jobs-Fair Activity | Conduct a jobs-fair activity for the youth | 100-150 youth Jobseekers attended (July 1, 2024) | Conducted a Jobs Fair during the founding anniversary. Female - 45 Male - 82 | 50000 | 50000 | Implemented
Inadequate financial assistance and livelihood program to the victims of calamity and disaster due to limited source of funds | Available source of funds for financial and livelihood assistance to victims of disaster and calamities | Livelihood Development Program and Financial Assistance | Provision of financial and livelihood assistance to victims of diaster and calamities. | Provided financial and livelihood assistance to victims of diaster and calamities. | Extended financial and livelihood assistance to calamity victims, focusing on sustainable solutions | 500000 | 275400 | Implemented
Increased maternal morbidity and mortality rate due to chronic health conditions | Complete prenatal and postnatal visits | Complete history taking and identification of high risk groups | Maternal and child health care program, prenatal, antenatal, postnatal care, 'Buntis Day' | 800 patients for prenatal examination and 800 patients for postpartum follow up | There were 604 pregnant women who received complete antenatal care and 587 postpartum women were given postpartum care. | 250000 | 250000 | Total number of accomplishments was only until the third quarter.
Increased number of animal bite patients being bitten by the stray dogs and cats | To provide anti-rabies vaccine/treatment to animal bite patient | Anti- Rabies treatment to animal bite patient | Procurement and Augmentation of Anti-Rabies | All animal patients treated depending on the category with anti-rabies after 3 to 4 sessions | 2,280 patients were vaccinated of anti-rabies vaccines | 800000 | 690000 | Implemented
Increased of patient with HIV seeking for help in ' Moncalinga ' HIV Treatment HUB'. | To provide primary care & treatment to person living with HIV | STI and HIV Program | Procurement and augmentation of HIV medicines and supplies | All patients with STI & HIV infection were provided with primary care and treatmentdepending on the severity & health status of the patient. | 16 patients were provided with primary care and treatment | 200000 | 200000 | Implemented
Lack of knowledge about Mental Health Awareness | To conduct a seminar that tackles Mental Health Awareness | Mental Health Awareness Seminar | Information Education Campaign on Mental Health | 100 teenagers concern Mental Health Awareness (May 11, 2024) | Not Implemented The PPA was included in the original draft of the Local Youth Development Plan, however, upon review, the certain PPA was removed from the final approved LYDP. Other PPAs were prioritized. | 20000 | 0 | Not implemented
Lack of knowledge about teenage pregnancy, and HIV/AIDS awareness | To conduct a seminar that tackles HIV/AIDS awareness and teenage pregnancy. | Teeanage Pregnancy and HIV/AIDS Awarenss Seminar | Information Education Campaign on HIV/AIDS Awareness | 100 teenagers concern for teenage pregnancy and HIV/AIDS Awareness (October 12, 2024) | Conducted a HIV/AIDS Awareness Campaign which was attended by 100 participants. Male: 59 Female: 41 | 20000 | 41000 | Implemented
Lack of knowledge on rescue and proper first aid application | For effective and efficient response during disasters | Capacity training | Conduct Emergency Medical Response Training; Basic Safety Water Training | Emergency Medical Response Training in 37 Barangays (total of 74 participants. | Instead of training the 37 barangays, emergency response training was provided to MDRRM Councils and LDRRMO personnel. ( total of 31 participants) MALE: 28 FEMALE: 3 | 250000 | 250000 | Since the barangay's EMR training remains valid through 2025, a different group of participants was selected.
Lack of knowledge on rescue and proper first aid application | To be prepared and to respond quickly in times of disaster to mention, communicable diseases | Information and dissemination campaign Capacity training | Conduct information and dissemination campaign drive thru posting online and signages to all barangays. | Conducted Information/Dissemination in 37 barangays of Moncada | Information and dissemination campaign was achieved across all 37 barangays. | 55000 | 55000 | Implemented
Lack of knowledge on rescue and proper first aid application | To save life; To provide awareness and educate people on proper first aid application and rescue operation | Establish and Sustainability Barangay DRRM Committee in every barangay ( RA 10121) | Advocacy information & education campaign adopting with the new normal | Conduct seminar/training on awareness and education of life saving strategies and planning on operations | The advocacy information and education campaign, adapted to the new normal, reached a broad audience including students from 7 schools, Barangay Officials from Brgy. Camp. 1 Sur, and BPATS personnel from all 37 barangays. | 300000 | 300000 | 100% implemented
Lack of relief goods and medical supplies during onslaught of disaster | Availability of food and medical supplies during onslaught of disaster | Stockpiling of relief goods and medical supplies | Provision of relief goods and medical supplies during the onslaught of disaster | Provided relief goods and medical supplies during the onslaught of disaster | Provided relief goods and medical supplies during the onslaught of disaster MALE:136 FEMALE:207 | 700000 | 211494 | 488,506 / Implemented The impact of the disaster was less severe than anticipated, affecting fewer families than expected so the allocated budget was not fully utilized. Many individuals and organizations stepped up to provide additional support, ensuring that the needs of the affected families were met. The timely provision of relief goods and medical supplies ensured immediate assistance to 343 disaster-affected families.
Lack of youth activities that will enhance youth leadership skills | To conduct leadership summit to enhance their leadership skills | Youth Leadership Summit | Conduct of different youth leadership activities | One leadership summit 200-250 participants.(December 20-22, 2024) | Conducted Leadership Training on June 29, 2024 Female - 29 Male - 11 | 120000 | 12217 | Implemented
Lecture/Symposium/ Seminar on Illegal Drugs in relation to PNP DOUBLE BARREL | To strengthen the advocacy campaign and raise the level of awareness of community on illegal drugs - To help the users and purshers refrain from engaging in illegal activities and to uplift their moral & welfare/spiritual enhancement and to train them in livelihood program/activities | Advocacy campaign | lectures/Awareness of the laws and penalties under RA 9165 to 37 brgy | conducted lectures to 37 brgys on laws under RA 9165 | Lecture/Symposium/ Seminar on Illegal Drugs were conducted to 37 Brgy | 150000 | 150000 | Implemented
Lecture/Symposium/Seminar on Illegal Drugs in relation to PNP DOUBLE BARREL | To strengthen the advocacy campaign and raise the level of awareness of community on illegal drugs - To help the users and purshers refrain from engaging in illegal activities and to uplift their moral & welfare/spiritual enhancement and to train them in livelihood program/activities | Advocacy campaign | Distribution of IEC Materials | 9000 flyers on the ill effect/kinds of ill drugs. | 9,500 Fliers were distributed to the community regarding the ill effect/kinds of drugs | 60000 | 60000 | Implemented
Lecture/Symposium/Seminar on Illegal Drugs in relation to PNP DOUBLE BARREL | To strengthen the advocacy campaign and raise the level of awareness of community on illegal drugs - To help the users and purshers refrain from engaging in illegal activities and to uplift their moral & welfare/spiritual enhancement and to train them in livelihood program/activities | OPLAN TOKHANG House Visitation | Re-Visitation of all illegal drug personalities. | 1161 visited OPLAN TAPHANG/OPLAN TOKHANG | Continous visitation to the PWUDs | 250000 | 250000 | Implemented
Lecture/Symposium/Seminar/livelihood programs on illegal drugs in relation to PNP DOUBLE BARREL to those entering in Bahay Pagbabago/Balay Silangan | To strengthen the advocacy campaign and raise the level of awareness of community on illegal drugs - To help the users and purshers refrain from engaging in illegal activities and to uplift their moral & welfare/spiritual enhancement and to train them in livelihood program/activities | Advocacy campaign | Conduct lectures/seminar on illegal drugs to PWUDS(people who use drugs), Reformist entering in Bahay Pagbabago/Balay Silangan to do livelihood activities | Bahay Pagbabago/Balay Silangan Reformist trained and developed their skill in livelihood activities | Continous lecture and Monitring to the reformist | 550000 | 550000 | Implemented
Lessen casualties on dogs and cats bite | To educate constituents on Rabies vaccination | Anti-Rabies Vaccination to dogs in the community | Purchase of Anti-Rabies Vaccine and Vaccination of dogs and cats | Purchased of Anti-Rabies Vaccine ( 7680 Total dog population in the community) Conducted lectures and distributed flyers on Rabies Vaccination | 50 bottles of Anti Rabies Vaccine | 180000 | 180000 | 450 total dog vaccinated
Lessen casualties on dogs and cats bite | To educate constituents on rabies vaccination | Anti-rabies vaccination to dogs and cats in the community | Information Education Campaign on Rabies Vaccination & distribution of flyers | Conducted lectures and distributed flyers | 350 pet owners benefited from the conduct of a lecture for the Awareness and Importance of vaccination to dogs. Although a total number of 966 pet owners were given materials on rabies vaccination. Male -432 Female- 534 | 50000 | 28552.8 | Active dissemination due to increase rabies cases.
Limited activities and programs concerning Senior Citizen health care | To Strengthen the advocacy campaign and raise the level of awareness on nutritional health related concerns. | Community Service | Distribution of Food Packs | Distributed food packs to all senior citizen in 37 barangay | PNP - 37 Community Outreach were conducted | 600000 | 600000 | Implemented
Low enrollment of high school students due to lack of school supplies needed | To increase the number of high school students to be enrolled on public schools | ' Balik- eSKwela Project' | Distribution of school supplies to different public high schools | 250 indigent high school students enrolled in public schools (July 28, 2024) | 75 Highschool Students from Baquero Norte Integrated School received School Supplies (July 29, 2024) Male - 41 Female - 34 | 200000 | 35250 | Implemented
Low equality and equitable participation across genders among youth | To strengthen and increase the awareness among youth regarding gender sensitivity | Gender-Sensitivity Orientation | Information Education Campaign on Gender-Sensitivity Education | 1 orientation/seminar on Gender-Sensitivity to be conducted. 100-150 participants. (September 14, 2024) | Not Implemented This certain PPA was removed from the final approved LYDP. The office, however, conducted a leadership training, which has a separate budgetary allotment, and other capacity building activities for the youth. | 30000 | 0 | Not Implemented
Low level of awareness regarding their rights and protection provided by the law | Enhanced the knowledge and awareness of the senior Citizens on their rights and other concern matters | Advocacy campaign | Lecture/ Dialogues to the Senior Citizen | Conducted lectures/ dialogues to senior citizens in 37 barangays to increase their awareness of their rights | PNP - A total of 48 dialogues and lectures were conducted to Senior Citizen | 25000 | 25000 | Implemented
Mainstreaming of climate and disaster risk based planning in local and barangay level | Addressing vulnerability in order to be resilient to climate change related hazards | Formulation and Adoption of responsive policy framework for reducing losses from climate change related | Mapping of areas prone to disaster and formulation of policy framework to reduce losses from climate change related disasters. | Formulated and adopted a responsive policy framework and reduced number of losses from climate change related disasters. | The mapping of areas prone to disaster and the development of a policy framework resulted in a reduction of losses from climate change- related disasters. | 200000 | 200000 | Implemented
Not fully organized Child Representatives in 37 barangays | Organization of Child Representatives in 37 barangays. | Data-banking of youth per barangay. | Enumeration & election of Officers of organized Child Representatives per barangay. | Well Organized Child Representative Officers and members in 37 barangays. | Child Representatives from the 37 barangays were organized with set of officers (22 female, 15 male) | 37000 | 37000 | implemented
Prevalence of underweight (malnourished) children 0-6 years old due to inadequate food intake, frequent illness /lack of knowlegde on proper nutirtion | To reduce prevalence of malnutrition among children 0-6 years from 89.06% in 2022 to 93% by the end of December 2024 | Operation Timbang and Supplemental Feeding Program,Delivery of Nutrition Services | Assessment and identification of underweight children thru Operation Timbang among 0-6 years old . | Conducted Operation Timbang to 200 underweight children identified and assessed | 5,778 pre-school children (0-59 mos) were weighed during the Operation Timbang from January to March 2024 | 150000 | 184279.9 | Implemented
Prevalence of underweight (malnourished) children 0-6 years old due to inadequate food intake, frequent illness /lack of knowlegde on proper nutirtion | To reduce prevalence of malnutrition among children 0-6 years from 89.06% in 2022 to 93% by the end of December 2024 | Operation Timbang and Supplemental Feeding Program,Delivery of Nutrition Services | Conduct of supplemental feeding program among underweight children | 70 underweight children became the recipients of feeding program to improved their health | 72 underweight children undergo dupplemental feeding | 1000000 | 1131220 | Implemented
Prevalence of VAWC cases, Trafficking in Persons, Cyber Pornorgraphy and other Gender Based Violence | To Strengthen the advocacy campaign and raise the level of awareness of the community on Violence Against Women and Children (VAWC) | Advocacy campaign | Dialoques with community partners LGU's and NGO's | Conducted dialogues with community partners, LGUs and NGOs to decrease crime incidents in 37 barangays | PNP -A total of 48 dialogues conducted from different Brangay , LGU, and NGOs MSWDO - Conducted advocacy campaign on Violence Against Women and Children together with PNP in the 37 barangays of Moncada during the celebration of Women's Month | 50000 | 50000 | Implemented
Prevalence of VAWC cases, Trafficking in Persons, Cyber Pornorgraphy and other Gender Based Violence | To Strengthen the advocacy campaign and raise the level of awareness of the community on Violence Against Women and Children (VAWC) | Advocacy campaign | School caravan re: Info drives on VAWC, TIP, Cyber Pornography and Other Sexual and GBVC on 12 school and 37 barangays | Conducted info dissemination in 12 schools and 37 barangayS | PNP- Atotal of 12 school and 37 brgy were visited and conducted information dessimination on VAWC cases, Trafficking in Persons, Cyber Pornorgraphy and other Gender Based Violence MSWDO - Conducted information dissemination in 12 schools and 37 barangays together with PNP. | 50000 | 50000 | Implemented
Prevalence of VAWC cases, Trafficking in Persons, Cyber Pornorgraphy and other Gender Based Violence | To Strengthen the advocacy campaign and raise the level of awareness of the community on Violence Against Women and Children (VAWC) | Advocacy campaign | 50 Info drives on VAWC, TIP, Cyber Pornography and Other Sexual and GBVC case utilizing the quad media | Gender Sensitivity Orientation/Training and 50 info drives conducted | PNP - A total of 55 information drive were conducted | 50000 | 50000 | Implemented
Prevalence of VAWC cases, Trafficking in Persons, Cyber Pornorgraphy and other Gender Based Violence | To Strengthen the advocacy campaign and raise the level of awareness of the community on Violence Against Women and Children (VAWC) | Advocacy campaign | Mobilization of 20 various community sectors to prevent and suppress Trafficking in Person | Mobilized 20 community sector in preventing and suppressing trafficking in person cases | PNP - Mobilized 20 stakeholders/NGOs and Advocacy Group | 100000 | 100000 | Implemented
Prevalence of VAWC cases, Trafficking in Persons, Cyber Pornorgraphy and other Gender Based Violence | To Strengthen the advocacy campaign and raise the level of awareness of the community on Violence Against Women and Children (VAWC) | Advocacy campaign | Production and distribution of IEC materials | 6000 flyers on VAWC, TIP, Cyber Pornography and other sexual violation given to the community | PNP - 6000 IEC materials were distributed on VAWC, TIP, Cyber Pornography and other sexual violation MSWDO - distributed 6,0000 IEC materials to the community with PNP | 100000 | 100000 | Implemented
Prevention of infection due to traditional circumcision and unaffordable services offered by private doctos/clinics to perform circumcission | To provide free circumcision to each qualified Moncadenos and to prevent them to perform the traditional circumcission method to lower the risk of infection | Operation Tuli | Screening by BHW and RHM and provision of free circumcision | 500 patients circumcised | 238 patients were circumcised on June 17, 2024 | 200000 | 200000 | There were only 238 patients who were circumcised because the other patients failed the screening.
Scattered garbages in the schools | To minimize the problem of scatterd garbages on the schools | Plastik Na Basura Mo, May Katumbas | Plastic wastes in schools will be exchanged with rice/school supplies | 8 public high schools participated in the project (October-December 2024) | Conducted Plastic Palit Bigas during the Founding Anniversary | 100000 | 100000 | Implemented
Unavailability of medicine and medical /dental supplies for the marginalized constituents | To provide medicines and medical/ dental supplies for the marginalized constituents | Inventory of needed medicines and medical/dental supplies | Procurement of needed medicines and medical/ dental supplies | Procured and provided buffer stock of medicines and medical/ dental supplies for the marginalized constituents | There were 8,270 patients who were given medicines for free. | 4000000 | 2209136.2 | Implemented
Vulnerability of Constituents specialy the youth on the use of illegal drugs | To help the constituents to prevent use of illegal drugs | Advocacy campaign | Conduct orientation/ lectures symposium pupils/ students, organization, NGOs, Businesses 15 schools and 37 barangay | Conducted drug symposium to 15 schools and in 37 barangays | 15 school and 37 Brgy were visted and conducted a Drug symposium | 108000 | 62769 | Implemented
Youths are unprepared when disaster occurrs | Increase knowledge of youths on disaster preparedness | 'KABATAANG ALERTO, LAGING HANDA 24' (Disaster Preparedness Seminar) | Workshop-Semianr on Disaster Preparedness | One Seminar/Orientation on Disaster Preparedness and Environment Awareness conducted 100-150 participants. ( Septmber 4, 2024) | Not Implemented The PPA did not meet the targeted number of participants for a separate seminar for disaster awareness. So, a few of the youth leaders attended the Disaster Awareness seminar conducted by the LDRRMO. No separate funding was used. | 50000 | 0 | Not Implemented
GAD Mandate
Difficulties experienced by the vulnerables and marginalized in the community in shouldering their expenses to be incurred during crisis situations | To help the vulnerables and marginalized sectors during crisis situations. | Assistance in Crisis situation (AICS) to vulnerable and marginalized individuals | Provision of financial assistance to families in crisi situation | 100 individuals in crisis situation assessed, validated and provided with financial assistance by the end of December 2024 | 336 individuals were validated and provided with financial assistance | 750000 | 508900 | Implemented
Increased number of Out of School youth due to lack of financial support | To encourage youth to enroll in Alternative learning system (ALS) and other institutions | Scholarship/ provision of Educational assistance | Assessment and validation of Youth's for Scholarship/ educational assistance. | 200 indigent Youths were validated and provided with scholarship/ educational assistance by the end of December 2024 | 157 youths were validated and provided with scholarship grants and educational assistance. | 1500000 | 1465945.5 | Implemented
Involvement of minors in crimes, child labor and early pregnancy due to truancy, underage drinking and difficult family relationships | To prevent youths in commiting crimes, child labor and early pregnancy | Organize recreational activities like indoor/outdoor games for the youth | Conduct recreational activities,indoor and outdoor games for youth | 111 Youth from the 37 barangays of Moncada participated in different recreational activities by the end of December 2024 | Organized a Fun Run and outdoor games during the Moncada Founding Anniversary which was participated by the Sangguniang Kabataan of the 37 barangays. | 150000 | 224555 | There was an increase of participants
Lack of additional benefits for Senior Citizens | To provide additional benefits for Senior Citizens | Identification of SC aged 90 years old by the first week of Oct. | Providing of longevity bonus to senior citizen aged 90 years old by the first week of October. | 30 Senior Citizen aged 90 years old provided with Longevity bonus. | 31 Senior Citizens aged 90 years old were providedwith Longevity bonus of P9,0000.00 each (25 female, 6 male) | 500000 | 279000 | implemented
Lack of additional benefits for Senior Citizens | To provide additional benefits for Senior Citizens . | Assessment and validation of Senior Citizens in 37 barangays of Moncada | Replication of Social Pension to Senior Citizens in the Municipality of Moncada. | 750 validated Senior Citizens from the 37 barangays provided with Social Pension. | 750 indigent senior citizens provided with monthly stipend of P500.00 (480 female, 270 male) | 1500000 | 4500000 | Instead of 166 pesos per month, the stipend was increased to 500 per month
Lack of additional educational support for youth | To provide temporary employment for students. | SPES or Immersion outreach Program | Assessment and validation of Youth's for SPES / Immersion outreach program. | 50 youth were hired and received grants for their temporary employment thru SPES / IOP . | 21 youth were hired and received grants for their temporary employment thru Immersion Outreach Program (IOP) and Government Internship Program (GIP) (14 female, 7 male) | 250000 | 250000 | implemented
Lack of financial assistance for senior citizens | To provide financial assistance to senior citizens | Provision of financial assistance to Senior Citizens | Assessment and validation Senior Citizens for the provision of financial assistance. | 50 Indigent Senior citizen provided with financial assistance. | 37 Indigent Senior Citizens provided with fiinancial Assistance thru AKAP | 300000 | 143500 | During the verfication, some are not qualified
Lack of livelihood skills training amongst PWD members | To provide livelihood skills training to PWD members | A. Dishwashing liquid and detergent making B. Candlemaking | Conduct livelihood training with kits on Dishwashing liquid and detergent making | 74 PWDs provided with livelihood training and kits on Dishwashing liquid and detergent making | 71 PWDs provided with livelihood and skills training on bread and coffee making (Male: 18, Female: 53) | 233000 | 200000 | implemented
Lack of opportunities and capacity for women to earn additional income for the family | To increase household income through livelihood programs | Conduct of Training and provision of capital for their livelihood program | Conduct initial assessment and validation for possible recipients and conduct livelihood training | 111 women were provided with livelihood assistance and participated livelihood training | 80 women participated in the livelihood training in noodle making and provided with tool kits | 555000 | 236299 | implemented
Lack of recreational activities for Senior Citizens | To increase health and fitness, as well as opportunities for socializing, for using skills and talents developed throughout their lifetime, and for learning new skills. | Indoor/ Outdoor activities for Senior Citizens | Conduct of recreational activities for Senior Citizens ( zumba, indoor and outdoor games etc) | 111 senior citizens participated in different recreational activities. | Organized a zumba during the Founding Anniversary. Conducted the Elderly Filipino Week on November 5, 2024 which was participated by 111 Senior Citizens. | 270000 | 270000 | Implemented
Lack of Team building activities for Child Development Workers | To improve camaraderie among the Child Development Workers | Capacity Building | Participation to the provincial & Regional Annual Assembly of CDW's. | 37 CDW's and 5 staff participated in the Annual Provincial & Regional CDW's Assembly. | 37 Child Development Workers and 5 Staff participated in the Annual Provincial CDWs Assembly. | 66000 | 50400 | implemented
Low competency among Child Development Workers | To improve skills and knowledge of Child Development Workers to do their job competently. | Capacity Building | Conduct Refresher course/ training for CDW's. | 37 Child Development workers trained. | 37 Child Development Workers attended/participated in the training of Project on Sustainable Training Assistance and Revitalized Teaching (S.T.A.R.T.) | 200000 | 200000 | Implemented
Low competency among youth | To enhance leadership skills among the youth | Capacity Building/ Leadership Training | Conduct Youth Leadership and Capability Building. | 111 Youths participated in the Youth Leadership training & Capability Building. | Conducted a Seminar (Youth Camp) and organized an assembly for youth organizations | 75000 | 99130 | Implemented
Low support to Solo -parents (RA 8972) Article IX Sec. 65 | To empower solo-parents through livelihood training and promote awareness regarding to Solo-parent guidelines. | Livelihood training and seminar regarding the solo-parents guidelines. | Conduct livelihood and Skills training in Dishwashing, Fabric conditioner and Soap making and provide kits and conduct forum regarding to Solo-parent guidelines. for solo-parents. | 74 Solo-parents participated the Livelihood training in Dishwashing, Fabric conditioner and Soap making and provided with kits and forum regarding to Solo-parent guidelines. | 37 Solo Parents attended/participated in the forum regarding solo parent guidelines during the Family Day and Thanksgiving celebration | 300000 | 315250 | implemented
Low support to Solo -parents (RA 8972) Article IX Sec. 65 | To provide educational assistance to the children of solo-parents. | Educational assistance program | Provision of educational assistance to the children of solo-parents. | 74 children of solo parents provided with educational assistance. | No accomplishment for this year. While there were applicants for the educational assistance program for children of solo parents, none met the specific eligibility requirements set for the program. However, to ensure that those deserving still received support, qualified applicants were redirected and screened under existing regular scholarship grants. | 250000 | 0 | Not implemented
Make functional Local Council for the Protection of Children (LCPC) | To promote responsible parenting | Child Protection Program | Conduct parent effectiveness Service in 37 Day care Centers of Moncada. | 1,200 children were enrolled & conducted Parent Effectiveness Service was participated by Day care Parents in the 37 Day care centers. | 1,100 Day Care Children enrolled in 37 Day Care Centers and their parents attended the Parent Effectiveness Service (PES) (520 female, 580 male) | 37000 | 37000 | implemented
Make functional Local Council for the Protection of Children (LCPC) | For updated and efficient uploading of Child information to the System | Child Protection Program | Conduct of technical assistance and Provision of Tablet-gadget for ECCD-IS Encoding,documentation to 37 ECCD Service providers | Provided technical assistance and program materials to 37 ECCD Service providers | Not implemented The activity was postponed because of delayed funds and problems with buying needed items. The partner agencies had not confirmed the tablet support, which delayed the technical help and documentation. | 535500 | 0 | Not Implemented
Make functional Local Council for the Protection of Children (LCPC) | To orient ECCD providers regarding the different Children Laws | Child Protection Program | Conduct Orientation on Different Laws of Children to ECCD Providers. | Conducted Orientation on Different Laws of Children to ECCD Providers. | 37 ECCD Providers attended the Orientation on Different Laws of Children during the conduct of Family Day and Thanksgiving Celebration | 100000 | 100000 | implemented
Make functional Local Council for the Protection of Children (LCPC) | To orient barangay VAWC Desk officers regarding laws on VAWC for proper assessment in their barangays | Child Protection Program | Conduct of Training on VAWC Desk Officers in 37 barangay. | Conducted Training on VAWC Desk Officers in 37 barangay. | 37 VAW/C Desk Officers participated in the conduct of 2-day Capacity Building | 100000 | 100000 | implemented
Make functional Local Council for the Protection of Children (LCPC) | To showcase the skills and enhance the talents of day care children | Child Protection Program | Conduct Children's Congress | 164 day care children participated in the Children's Congress. | 126 day care children participated in the conduct of Children's Congress | 100000 | 119134 | implemented
Not fully organized Solo-parent in 37 barangays | Organization of Solo-parents in 37 barangays. | Data-banking of solo-parents per barangay. | Enumeration & election of Officers of organized Solo-parents per barangay. | Well Organized Solo-Parent Officers and members in 37 barangays. | Solo Parents from the 37 barangays were organized with set of officer (36 female, 1 male) | 37000 | 37000 | implemented
Poor access of PWDs to social welfare programs | To strengthen awareness of Persons with Disabilities on their rights for increased self-worth | Provision of financial assistance | Provide financial assistance to poor PWDs | Indigent PWDs provided with financial assistance | 83 indigents were given financial assistance | 181000 | 167000 | Implemented
Poor access of PWDs to social welfare programs | To strengthen awareness of Persons with Disabilities on their rights for increased self-worth | Provision of financial assistance | Provide medical/burial assistance to poor PWDs | 37 indigent PWDs provided with medical/burial assistance | Medical assistance were given to 37 indigents | 250000 | 250000 | Implemented
RA 7277, Section 2(e) To facilitate integration of disabled persons into the mainstreaming of society, the State shall advocate for and encourage respect for disabled persons. The State shall exert all efforts to remove all social, cultural, economic, environmental and attitudinal barriers that are prejudicial to disable persons. | To strengthen awareness of Persons with Disabilities on their rights for increased self-worth | Provision of Meal and Transportation Allowance | Provide of Meal and Transportation Allowance to Barangay PWD Presidents on Municipal, Provincial and Regional Meetings | 37 Barangay PWD Presidents provided with Meal and Transportation Allowance on Municipal, Provincial and Regional Meetings | 37 Barangay PWD Presidents provided with Meal and Transportation Allowance on Municipal, Provincial and Regional Meetings (Male:22, Female: 15) | 87000 | 126000 | implemented
RA 7277, Section 2(e) To facilitate integration of disabled persons into the mainstreaming of society, the State shall advocate for and encourage respect for disabled persons. The State shall exert all efforts to remove all social, cultural, economic, environmental and attitudinal barriers that are prejudicial to disable persons. | To strengthen awareness of Persons with Disabilities on their rights for increased self-worth | PWD Year-End General Assembly and Gift Giving | Conduct of PWD Year-End General Assembly and Gift Giving | Number of 111 PWDs attended on Year-End General Assembly and Gift Giving | 37 Barangay PWD Presidents provided with Meal and Transportation Allowance on Municipal, Provincial and Regional Meetings (Male:22, Female: 15) | 50000 | 50000 | implemented
RA 7277, Section 2(e) To facilitate integration of disabled persons into the mainstreaming of society, the State shall advocate for and encourage respect for disabled persons. The State shall exert all efforts to remove all social, cultural, economic, environmental and attitudinal barriers that are prejudicial to disable persons. | To strengthen awareness of Persons with Disabilities on their rights for increased self-worth | Capacity building | Conduct capacity building like workshop with outdoor activities | 74 PWDs participatued on capacity building like workshop with outdoor activities | Organized a paralympics during the Founding Anniversary. Various games were conducted for the PWD community. This was participated by 37 PWDs. Male-22, Female-15 | 30000 | 31400 | Implemented
RA 7277, Section 2(e) To facilitate integration of disabled persons into the mainstreaming of society, the State shall advocate for and encourage respect for disabled persons. The State shall exert all efforts to remove all social, cultural, economic, environmental and attitudinal barriers that are prejudicial to disable persons. | To strengthen awareness of Persons with Disabilities on their rights for increased self-worth | Lakbay-Aral | Conduct Lakbay-Aral to be able to learn best practices on implementation of PWD programs, projects and actitivities. | 37 PWDs participated on capacity building like workshop with outdoor activities | Not accomplished this year. The conduct of the Lakbay-Aral activity was not implemented as originally planned due to the prioritization of other programs and activities within the same timeframe. Key personnel and resources were redirected to support other priority initiatives, making it difficult to schedule and coordinate the learning visit. | 50000 | 0 | Not implemented
RA 7277, Section 2(e) To facilitate integration of disabled persons into the mainstreaming of society, the State shall advocate for and encourage respect for disabled persons. The State shall exert all efforts to remove all social, cultural, economic, environmental and attitudinal barriers that are prejudicial to disable persons. | To strengthen awareness of Persons with Disabilities on their rights for increased self-worth | Paralympics | Participate during Provincial Paralympics | 25 PWDs participated on Paralympics | 16 PWDs participated on March 7, 2024 in celebration of Kanlahi Festival (Male: 9, Female:7) | 30000 | 27300 | implemented
RA 7277, Section 2(e) To facilitate integration of disabled persons into the mainstreaming of society, the State shall advocate for and encourage respect for disabled persons. The State shall exert all efforts to remove all social, cultural, economic, environmental and attitudinal barriers that are prejudicial to disable persons. | To strengthen awareness of Persons with Disabilities on their rights for increased self-worth | Provision of Uniforms | Provide uniforms to 37 Barangay PWD Presidents to be used during monthly meetings and other PWD related activities | 37 Barangay PWD Presidents provided uniforms to be used during monthly meetings and other PWD related activities | 37 Barangay PWD Presidents provided uniforms to be used during monthly meetings and other PWD related activities (Male: 22, Female: 15) | 18500 | 19425 | implemented
RA 7277, Section 2(e) To facilitate integration of disabled persons into the mainstreaming of society, the State shall advocate for and encourage respect for disabled persons. The State shall exert all efforts to remove all social, cultural, economic, environmental and attitudinal barriers that are prejudicial to disable persons. | To strengthen awareness of Persons with Disabilities on their rights for increased self-worth | Provision of assistive devices | Provide assistive devices to PWD members | 37 PWDs provided assistive devices | 12 Wheelchairs were provided to PWDs from the different barangays. | 100000 | 100000 | Implemented
Sec. 30 of MCW Economic Rights and Power a) WOMEN | To encourage women to participate in programs to increase their knowledge and their awareness regarding their rights and other services program for their protection. | Capacity Building | Conduct of Women's Month Celebration with Seminar on Rights of Women' | Conducted lecture(Forum on Magna Carta of Women participated by 200 women from diffirent sectors | 250 women participated in the conduct of lecture/forum on Magna Carta of Women during the Municipal Women's Month celebration. | 200000 | 200000 | Implemented
Sub-total A | [5 empty] | 20800000 | 19255607.4
ORGANIZATION-FOCUSED
Gender Issue
Increased flood areas due to clogged canals and creeks | Reduced flood areas within the Municipality | Monitoring and maintenance of clean and unclogged canals and creeks | Conduct regular de-clogging of canals and dredging of creeks | Reduced number of flooded areas within the municipality. | After dredging demonstrated a significant increase in the depth and width of the waterways benefiting communities, businesses, and the environment. | 250000 | 494300 | Implemented
Low level of awareness on Gender mainstreaming | Increase knowledge of LGU GFPS and TWG on Gender Maintreaming in the implementation of the GPB PPAs and the utilization of the GAD budget | Capacity Building for GFPS | Conduct trainig/seminar on Gender Analysis and Tools, GAD Planning and Budgeting Guidelines | Conducted seminar on Mainstreaming Gender in Program and Project Dev't. using HGDG/PIMME/FIMME Tool participated with GFPS committee and TWG | Conducted a seminar-workshop on December 18-19, 2024 on the topic of Gender and Development Orientation, Gender Analysis using the different GAD Tools participated by 50 member of the GFPS | 75000 | 78250 | Implemented
GAD Mandate
Inefficient delivery of services of personnels due to lack of office facilities and equipments | Effective and efficient delivery of services | Provision of Equipment & facilities. | Procurement of office facilities, equipments for the use of MSWD Office such as: computer sets,Cabinets, children's toys, Digital camera for photodocumentation, Projectors and White Board, Xerox Machine | Purchased facilities and Equipments to MSWD Office by the end of December 2024 | Purchased Furnitures and Fixtures for the newly built extension of the MSWD office and also purchased and installed three (3) airconditioning units for the MSWD Office. | 500000 | 1224111.25 | Implemented
lack of additional benefits for senior citizens, the Home Care Support Services for Senior Citizens (HCSSSC) | To encourage Senior Citizens to participate in programs to increase their knowledge and their awareness regarding their rights and other services program for their protection. | organize the project for the vulnerable and marginalized SCs | Conduct of Skills Enhancement training & capability Building of HCSSSC Project | Conducted Skills Enhancement training and capability Building participated by 37 volunteers | Not accomplished for the year. The activity was not accomplished because of schedule conflicts with the speakers and participants. Only two volunteers were able to attend a sponsored training on such matter. No additional funding was used. | 250000 | 0 | Not Implemented
lack of additional benefits for senior citizens, the Reporting System and Prevention Program for Elderly Abuse Cases ReSPPEC) | To encourage Senior Citizens to participate in programs to increase their knowledge and their awareness regarding their rights and other services program for their protection. | organize the project for the vulnerable and marginalized SCs | Conduct of Skills Enhancement training & capability Building of ReSPPEC Project | Conducted Skills Enhancement training and capability Building participated by 37 volunteers | No accomplishment for the year. The activity was not implemented because local funds and plans were changed based on new regional instructions. There were also problems getting participants and finishing the training modules on time. | 500000 | 0 | Not Implemented
Lack of knowledge of SC's regarding Senior Citizen's law s, their benefits and privileges due to lack of participation in elderly events | To encourage Senior Citizens to participate in programs that improves their knowledge and their awareness regarding their rights , programs and services for their protection. | Capacity Building | Conduct Elderly week Celebration (Municipal,Provincial,Regional)with Forum on Senior Citizen Laws | Conducted Elderly Week celebration with Forum on Senior Citizen Laws participated by 111 Senior Citizens by the end of November 2024 | Conducted Elderly Week Celebration and Ulirang Nakatatanda participated by 111 Senior Citizens. | 350000 | 350000 | implemented
Lack of support for the preparation on the Search for the Best Day Care Center/Worker. | Augmentation to the selected Day care Center/Worker | Provide foods/materials to be needed in the Search for Best Day Care Center/Worker | Search for the Best Day Care Center/ Worker | Provided instructional materials,and renovation of the selected Day Care Center by the end of December 2024 | 1 Day Care Center (San Roque) was renovated and provided instructional materials | 1000000 | 2598000 | implemented
Low monthly compensation of Child Development Workers due to low honoraria | Augmentation on the monthly Honoraria of Child Development Workers. | Human resource development | Request LGU to increase the Honoraria of Child Development Workers | 37 CDW's provided with increased honoraria by the end of December 2024 | 36 Child Development Workers were provided with increase in honoraria | 500000 | 500000 | implemented
Not fully functinal Day Care centers due to lack of requirements needed for standard licencing and accreditation. | Fully functional Day care Centers in 37 barangays | Augmentation of LGU for the improvement of 37 Day care Centers | Provide facilities such us : -Window screens,singnages,cabinets,furnitures & fixtures,learning materials. | 37 Day Care Centers were fully functional and accredited. | 37 Day Care Centers were fully functional and accredited | 500000 | 500000 | implemented
Not fully organized women's group in 37 barangays | To organize KALIPI- barangay chapter in 37 barangays. | Databanking of women in 37 barangays | Conduct re-organization of Women's group, election of officers and monthly meeting | 37 Barangays established Organized Women's Group | 37 barangays have established organized women's groups known as KALIPI | 75000 | 75000 | Implemented
Not fully organized women's group in 37 barangays | To empower women in different aspects of life | Women's Assembly | Conduct General Assembly of Organized Women. | Conducted General Assembly of Women participated by 111 members of organized women. | a general assembly was conducted for the organized women from the 37 barangays with a total of 80 participants | 100000 | 100000 | Implemented
Proclamation No. 361 Declaring the Third Week of July as National Disability Prevention and Rehabilitation Week | To strengthen awareness of Persons with Disabilities on their rights for increased self-worth | National Disability Prevention and Rehabilitation Week | Conduct NDPR Week celebration and Forum on PWD Guidelines | 111 PWDs participated during NDPR Week celebration and Forum on PWD Guidelines | 14 PWDs participated during NDPR Week celebration and Forum on PWD Guidelines (Male: 6, Female: 8) | 100000 | 100000 | implemented
Sub-total B | [5 empty] | 4200000 | 6019661.25
ATTRIBUTED PROGRAMS
Title of LGU Program or Project (10) |  |  |  |  | HGDG PIMME/ FIMME Score (11) | Total Annual Program/ Project Cost or Expenditure (12) | GAD Attributed Program/Project Cost or Expenditure (13) | Variance or Remarks (14)
Construction of 3 classroom School Bldg. |  |  |  |  | 16.67 | 4753050 | 3564787.5 | Increased of 75.74% of the Approved GAD Budget to completed the physical structure thru 20% DF
3564787.5
Sub-total C | [6 empty] | 28840056.15
Grand TOTAL (A+B+C)
Prepared by: KRIZZIA ROSE T. CUSTODIO GFPS Focal Person |  | Prepared by: ESTELITA M. AQUINO Local Chief Executive |  |  |  | DATE: 30/04/2025

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
46